## Summary
Parade of Trades – Replication Summary
n_reps | 30
seed_base | 100
mode | classic
total_units | 100
takt_rate
standby_capacity | 0
staggered | FALSE
metric | n | mean | std | min | p25 | median | p75 | max
duration | 30 | 25.6 | 1.714 | 23 | 24 | 26 | 27 | 30
throughput | 30 | 3.923 | 0.2599 | 3.3333 | 3.7037 | 3.8462 | 4.1667 | 4.3478
total_idle | 30 | 86.9 | 29.6826 | 42 | 70 | 79 | 102 | 160
peak_wip | 30 | 22.3 | 8.2133 | 8 | 16 | 22.5 | 28 | 45
total_standby | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Time on site by trade
trade | n | mean | std | min | p25 | median | p75 | max
time_on_site[Pemasangan Bekisting] | 30 | 21.1 | 2.2027 | 17 | 19 | 20.5 | 23 | 26
time_on_site[Pemasangan Tulangan] | 30 | 22.7 | 1.9853 | 19 | 22 | 23 | 24 | 26
time_on_site[Pengecoran Beton] | 30 | 23.9333 | 1.5071 | 22 | 23 | 23 | 24.75 | 28
time_on_site[Pembongkaran Bekisting] | 30 | 24.7 | 1.6846 | 22 | 23.25 | 24 | 26 | 28
time_on_site[Finishing Lantai] | 30 | 25.6 | 1.714 | 23 | 24 | 26 | 27 | 30

## Replications
rep | seed | duration | throughput | total_idle | peak_wip | total_standby | tos_t1 | idle_t1 | util_t1 | stby_t1 | tos_t2 | idle_t2 | util_t2 | stby_t2 | tos_t3 | idle_t3 | util_t3 | stby_t3 | tos_t4 | idle_t4 | util_t4 | stby_t4 | tos_t5 | idle_t5 | util_t5 | stby_t5
1 | 100 | 24 | 4.1667 | 50 | 24 | 0 | 20 | 0 | 1 | 0 | 23 | 17 | 0.8547 | 0 | 23 | 13 | 0.885 | 0 | 24 | 12 | 0.8929 | 0 | 24 | 8 | 0.9259 | 0
2 | 101 | 28 | 3.5714 | 160 | 20 | 0 | 24 | 0 | 1 | 0 | 24 | 36 | 0.7353 | 0 | 28 | 40 | 0.7143 | 0 | 28 | 36 | 0.7353 | 0 | 28 | 48 | 0.6757 | 0
3 | 102 | 26 | 3.8462 | 61 | 24 | 0 | 20 | 4 | 0.9615 | 0 | 21 | 11 | 0.9009 | 0 | 23 | 5 | 0.9524 | 0 | 25 | 19 | 0.8403 | 0 | 26 | 22 | 0.8197 | 0
4 | 103 | 26 | 3.8462 | 85 | 24 | 0 | 20 | 0 | 1 | 0 | 22 | 6 | 0.9434 | 0 | 23 | 9 | 0.9174 | 0 | 24 | 24 | 0.8065 | 0 | 26 | 46 | 0.6849 | 0
5 | 104 | 30 | 3.3333 | 86 | 24 | 0 | 24 | 4 | 0.9615 | 0 | 26 | 6 | 0.9434 | 0 | 26 | 30 | 0.7692 | 0 | 28 | 20 | 0.8333 | 0 | 30 | 26 | 0.7937 | 0
6 | 105 | 24 | 4.1667 | 74 | 32 | 0 | 18 | 2 | 0.9804 | 0 | 24 | 0 | 1 | 0 | 24 | 24 | 0.8065 | 0 | 24 | 28 | 0.7812 | 0 | 24 | 20 | 0.8333 | 0
7 | 106 | 26 | 3.8462 | 77 | 28 | 0 | 19 | 1 | 0.9901 | 0 | 22 | 2 | 0.9804 | 0 | 22 | 14 | 0.8772 | 0 | 26 | 26 | 0.7937 | 0 | 26 | 34 | 0.7463 | 0
8 | 107 | 24 | 4.1667 | 42 | 32 | 0 | 19 | 1 | 0.9901 | 0 | 19 | 13 | 0.885 | 0 | 22 | 10 | 0.9091 | 0 | 22 | 18 | 0.8475 | 0 | 24 | 0 | 1 | 0
9 | 108 | 27 | 3.7037 | 104 | 20 | 0 | 22 | 2 | 0.9804 | 0 | 26 | 10 | 0.9091 | 0 | 26 | 30 | 0.7692 | 0 | 27 | 29 | 0.7752 | 0 | 27 | 33 | 0.7519 | 0
10 | 109 | 27 | 3.7037 | 77 | 28 | 0 | 20 | 0 | 1 | 0 | 23 | 1 | 0.9901 | 0 | 24 | 20 | 0.8333 | 0 | 25 | 27 | 0.7874 | 0 | 27 | 29 | 0.7752 | 0
11 | 110 | 27 | 3.7037 | 132 | 12 | 0 | 26 | 6 | 0.9434 | 0 | 26 | 34 | 0.7463 | 0 | 26 | 30 | 0.7692 | 0 | 27 | 25 | 0.8 | 0 | 27 | 37 | 0.7299 | 0
12 | 111 | 26 | 3.8462 | 82 | 28 | 0 | 19 | 1 | 0.9901 | 0 | 22 | 6 | 0.9434 | 0 | 23 | 25 | 0.8 | 0 | 24 | 24 | 0.8065 | 0 | 26 | 26 | 0.7937 | 0
13 | 112 | 23 | 4.3478 | 79 | 16 | 0 | 20 | 0 | 1 | 0 | 20 | 4 | 0.9615 | 0 | 23 | 29 | 0.7752 | 0 | 23 | 21 | 0.8264 | 0 | 23 | 25 | 0.8 | 0
14 | 113 | 24 | 4.1667 | 64 | 20 | 0 | 20 | 0 | 1 | 0 | 22 | 18 | 0.8475 | 0 | 23 | 9 | 0.9174 | 0 | 23 | 13 | 0.885 | 0 | 24 | 24 | 0.8065 | 0
15 | 114 | 25 | 4 | 119 | 12 | 0 | 24 | 4 | 0.9615 | 0 | 24 | 28 | 0.7812 | 0 | 24 | 44 | 0.6944 | 0 | 24 | 36 | 0.7353 | 0 | 25 | 7 | 0.9346 | 0
16 | 115 | 24 | 4.1667 | 56 | 16 | 0 | 23 | 1 | 0.9901 | 0 | 23 | 17 | 0.8547 | 0 | 23 | 17 | 0.8547 | 0 | 23 | 9 | 0.9174 | 0 | 24 | 12 | 0.8929 | 0
17 | 116 | 23 | 4.3478 | 76 | 24 | 0 | 19 | 5 | 0.9524 | 0 | 22 | 6 | 0.9434 | 0 | 22 | 6 | 0.9434 | 0 | 22 | 26 | 0.7937 | 0 | 23 | 33 | 0.7519 | 0
18 | 117 | 26 | 3.8462 | 148 | 12 | 0 | 22 | 6 | 0.9434 | 0 | 25 | 7 | 0.9346 | 0 | 25 | 39 | 0.7194 | 0 | 26 | 54 | 0.6494 | 0 | 26 | 42 | 0.7042 | 0
19 | 118 | 28 | 3.5714 | 74 | 35 | 0 | 19 | 1 | 0.9901 | 0 | 20 | 8 | 0.9259 | 0 | 24 | 4 | 0.9615 | 0 | 27 | 21 | 0.8264 | 0 | 28 | 40 | 0.7143 | 0
20 | 119 | 26 | 3.8462 | 69 | 20 | 0 | 22 | 6 | 0.9434 | 0 | 22 | 6 | 0.9434 | 0 | 24 | 12 | 0.8929 | 0 | 25 | 23 | 0.813 | 0 | 26 | 22 | 0.8197 | 0
21 | 120 | 26 | 3.8462 | 136 | 8 | 0 | 24 | 0 | 1 | 0 | 26 | 26 | 0.7937 | 0 | 26 | 34 | 0.7463 | 0 | 26 | 42 | 0.7042 | 0 | 26 | 34 | 0.7463 | 0
22 | 121 | 27 | 3.7037 | 73 | 45 | 0 | 17 | 3 | 0.9709 | 0 | 19 | 5 | 0.9524 | 0 | 26 | 6 | 0.9434 | 0 | 26 | 34 | 0.7463 | 0 | 27 | 25 | 0.8 | 0
23 | 122 | 24 | 4.1667 | 91 | 12 | 0 | 23 | 1 | 0.9901 | 0 | 23 | 33 | 0.7519 | 0 | 23 | 13 | 0.885 | 0 | 24 | 20 | 0.8333 | 0 | 24 | 24 | 0.8065 | 0
24 | 123 | 27 | 3.7037 | 105 | 16 | 0 | 23 | 1 | 0.9901 | 0 | 23 | 21 | 0.8264 | 0 | 23 | 9 | 0.9174 | 0 | 23 | 37 | 0.7299 | 0 | 27 | 37 | 0.7299 | 0
25 | 124 | 24 | 4.1667 | 60 | 20 | 0 | 22 | 6 | 0.9434 | 0 | 23 | 9 | 0.9174 | 0 | 23 | 5 | 0.9524 | 0 | 24 | 12 | 0.8929 | 0 | 24 | 28 | 0.7812 | 0
26 | 125 | 24 | 4.1667 | 92 | 12 | 0 | 23 | 5 | 0.9524 | 0 | 23 | 21 | 0.8264 | 0 | 23 | 25 | 0.8 | 0 | 23 | 29 | 0.7752 | 0 | 24 | 12 | 0.8929 | 0
27 | 126 | 23 | 4.3478 | 44 | 28 | 0 | 19 | 1 | 0.9901 | 0 | 20 | 4 | 0.9615 | 0 | 23 | 1 | 0.9901 | 0 | 23 | 21 | 0.8264 | 0 | 23 | 17 | 0.8547 | 0
28 | 127 | 26 | 3.8462 | 96 | 28 | 0 | 22 | 6 | 0.9434 | 0 | 23 | 9 | 0.9174 | 0 | 24 | 8 | 0.9259 | 0 | 25 | 35 | 0.7407 | 0 | 26 | 38 | 0.7246 | 0
29 | 128 | 26 | 3.8462 | 79 | 28 | 0 | 19 | 1 | 0.9901 | 0 | 21 | 11 | 0.9009 | 0 | 23 | 21 | 0.8264 | 0 | 24 | 16 | 0.8621 | 0 | 26 | 30 | 0.7692 | 0
30 | 129 | 27 | 3.7037 | 116 | 21 | 0 | 21 | 3 | 0.9709 | 0 | 24 | 0 | 1 | 0 | 26 | 30 | 0.7692 | 0 | 26 | 42 | 0.7042 | 0 | 27 | 41 | 0.7092 | 0

## Config
# | name | low | high | mean
1 | Pemasangan Bekisting | 3 | 7 | 5
2 | Pemasangan Tulangan | 3 | 7 | 5
3 | Pengecoran Beton | 3 | 7 | 5
4 | Pembongkaran Bekisting | 3 | 7 | 5
5 | Finishing Lantai | 3 | 7 | 5