## Summary
Parade of Trades – Run Summary
seed | 42
total_units | 100
mode | takt=5, standby=1
takt_rate | 5
standby_capacity | 1
staggered_mobilization | FALSE
duration | 20
ideal_duration | 18.1818
throughput | 5
total_idle | 27
total_standby | 55
peak_simultaneous_wip | 5

## Trades
# | name | low | high | executions | production | idle | utilization | finish | time_on_site | standby_used | effective_capacity
1 | Pemasangan Bekisting | 4 | 6 | 19 | 100 | 2 | 0.98039 | 19 | 19 | 12 | 102
2 | Pemasangan Tulangan | 4 | 6 | 19 | 100 | 5 | 0.95238 | 19 | 19 | 9 | 105
3 | Pengecoran Beton | 4 | 6 | 19 | 100 | 4 | 0.96154 | 19 | 19 | 10 | 104
4 | Pembongkaran Bekisting | 4 | 6 | 20 | 100 | 11 | 0.9009 | 20 | 20 | 9 | 111
5 | Finishing Lantai | 4 | 6 | 20 | 100 | 5 | 0.95238 | 20 | 20 | 15 | 105

## History
period | raw_remaining | cap_1 | prod_1 | idle_1 | cum_1 | eff_1 | stby_1 | cap_2 | prod_2 | idle_2 | cum_2 | eff_2 | stby_2 | cap_3 | prod_3 | idle_3 | cum_3 | eff_3 | stby_3 | cap_4 | prod_4 | idle_4 | cum_4 | eff_4 | stby_4 | cap_5 | prod_5 | idle_5 | cum_5 | eff_5 | stby_5 | buffer_1 | buffer_2 | buffer_3 | buffer_4
1 | 95 | 4 | 5 | 0 | 5 | 5 | 1 | 4 | 5 | 0 | 5 | 5 | 1 | 6 | 5 | 1 | 5 | 6 | 0 | 4 | 5 | 0 | 5 | 5 | 1 | 4 | 5 | 0 | 5 | 5 | 1 | 0 | 0 | 0 | 0
2 | 90 | 4 | 5 | 0 | 10 | 5 | 1 | 4 | 5 | 0 | 10 | 5 | 1 | 4 | 5 | 0 | 10 | 5 | 1 | 6 | 5 | 1 | 10 | 6 | 0 | 4 | 5 | 0 | 10 | 5 | 1 | 0 | 0 | 0 | 0
3 | 85 | 4 | 5 | 0 | 15 | 5 | 1 | 4 | 5 | 0 | 15 | 5 | 1 | 4 | 5 | 0 | 15 | 5 | 1 | 4 | 5 | 0 | 15 | 5 | 1 | 4 | 5 | 0 | 15 | 5 | 1 | 0 | 0 | 0 | 0
4 | 80 | 4 | 5 | 0 | 20 | 5 | 1 | 6 | 5 | 1 | 20 | 6 | 0 | 4 | 5 | 0 | 20 | 5 | 1 | 6 | 5 | 1 | 20 | 6 | 0 | 6 | 5 | 1 | 20 | 6 | 0 | 0 | 0 | 0 | 0
5 | 75 | 4 | 5 | 0 | 25 | 5 | 1 | 4 | 5 | 0 | 25 | 5 | 1 | 6 | 5 | 1 | 25 | 6 | 0 | 6 | 5 | 1 | 25 | 6 | 0 | 6 | 5 | 1 | 25 | 6 | 0 | 0 | 0 | 0 | 0
6 | 70 | 4 | 5 | 0 | 30 | 5 | 1 | 4 | 5 | 0 | 30 | 5 | 1 | 6 | 5 | 1 | 30 | 6 | 0 | 4 | 5 | 0 | 30 | 5 | 1 | 4 | 5 | 0 | 30 | 5 | 1 | 0 | 0 | 0 | 0
7 | 64 | 6 | 6 | 0 | 36 | 6 | 0 | 4 | 5 | 0 | 35 | 5 | 1 | 6 | 5 | 1 | 35 | 6 | 0 | 6 | 5 | 1 | 35 | 6 | 0 | 6 | 5 | 1 | 35 | 6 | 0 | 1 | 0 | 0 | 0
8 | 59 | 4 | 5 | 0 | 41 | 5 | 1 | 6 | 6 | 0 | 41 | 6 | 0 | 4 | 5 | 0 | 40 | 5 | 1 | 6 | 5 | 1 | 40 | 6 | 0 | 4 | 5 | 0 | 40 | 5 | 1 | 0 | 1 | 0 | 0
9 | 53 | 6 | 6 | 0 | 47 | 6 | 0 | 6 | 6 | 0 | 47 | 6 | 0 | 4 | 5 | 0 | 45 | 5 | 1 | 4 | 5 | 0 | 45 | 5 | 1 | 4 | 5 | 0 | 45 | 5 | 1 | 0 | 2 | 0 | 0
10 | 48 | 4 | 5 | 0 | 52 | 5 | 1 | 6 | 5 | 1 | 52 | 6 | 0 | 4 | 5 | 0 | 50 | 5 | 1 | 4 | 5 | 0 | 50 | 5 | 1 | 4 | 5 | 0 | 50 | 5 | 1 | 0 | 2 | 0 | 0
11 | 42 | 6 | 6 | 0 | 58 | 6 | 0 | 6 | 6 | 0 | 58 | 6 | 0 | 6 | 6 | 0 | 56 | 6 | 0 | 6 | 6 | 0 | 56 | 6 | 0 | 4 | 5 | 0 | 55 | 5 | 1 | 0 | 2 | 0 | 1
12 | 36 | 6 | 6 | 0 | 64 | 6 | 0 | 6 | 6 | 0 | 64 | 6 | 0 | 4 | 5 | 0 | 61 | 5 | 1 | 6 | 5 | 1 | 61 | 6 | 0 | 4 | 5 | 0 | 60 | 5 | 1 | 0 | 3 | 0 | 1
13 | 31 | 4 | 5 | 0 | 69 | 5 | 1 | 4 | 5 | 0 | 69 | 5 | 1 | 4 | 5 | 0 | 66 | 5 | 1 | 6 | 5 | 1 | 66 | 6 | 0 | 6 | 6 | 0 | 66 | 6 | 0 | 0 | 3 | 0 | 0
14 | 25 | 6 | 6 | 0 | 75 | 6 | 0 | 4 | 5 | 0 | 74 | 5 | 1 | 6 | 6 | 0 | 72 | 6 | 0 | 4 | 5 | 0 | 71 | 5 | 1 | 4 | 5 | 0 | 71 | 5 | 1 | 1 | 2 | 1 | 0
15 | 20 | 4 | 5 | 0 | 80 | 5 | 1 | 6 | 6 | 0 | 80 | 6 | 0 | 6 | 6 | 0 | 78 | 6 | 0 | 6 | 6 | 0 | 77 | 6 | 0 | 4 | 5 | 0 | 76 | 5 | 1 | 0 | 2 | 1 | 1
16 | 15 | 4 | 5 | 0 | 85 | 5 | 1 | 6 | 5 | 1 | 85 | 6 | 0 | 4 | 5 | 0 | 83 | 5 | 1 | 6 | 6 | 0 | 83 | 6 | 0 | 6 | 6 | 0 | 82 | 6 | 0 | 0 | 2 | 0 | 1
17 | 9 | 6 | 6 | 0 | 91 | 6 | 0 | 4 | 5 | 0 | 90 | 5 | 1 | 6 | 6 | 0 | 89 | 6 | 0 | 4 | 5 | 0 | 88 | 5 | 1 | 4 | 5 | 0 | 87 | 5 | 1 | 1 | 1 | 1 | 1
18 | 3 | 6 | 6 | 0 | 97 | 6 | 0 | 6 | 6 | 0 | 96 | 6 | 0 | 6 | 6 | 0 | 95 | 6 | 0 | 6 | 6 | 0 | 94 | 6 | 0 | 4 | 5 | 0 | 92 | 5 | 1 | 1 | 1 | 1 | 2
19 | 0 | 4 | 3 | 2 | 100 | 5 | 1 | 6 | 4 | 2 | 100 | 6 | 0 | 4 | 5 | 0 | 100 | 5 | 1 | 4 | 5 | 0 | 99 | 5 | 1 | 4 | 5 | 0 | 97 | 5 | 1 | 0 | 0 | 1 | 2
20 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 4 | 1 | 4 | 100 | 5 | 1 | 4 | 3 | 2 | 100 | 5 | 1 | 0 | 0 | 0 | 0

## Buffers
interface | from | to | max_wip
1 | Pemasangan Bekisting | Pemasangan Tulangan | 1
2 | Pemasangan Tulangan | Pengecoran Beton | 3
3 | Pengecoran Beton | Pembongkaran Bekisting | 1
4 | Pembongkaran Bekisting | Finishing Lantai | 2